Crux Innovation Implementation Outline: 
A Three-Year Strategic Implementation Plan for a Flipped-Lab Imaging Library in Cardiac Sonography Education

Liberty Cowden
Lamar University
EDLD 5305 D31 _OL
Dr. Fredy Padovan
May 4, 2026

Crux Innovation Implementation Outline:

A Three-Year Strategic Implementation Plan for a Flipped-Lab Imaging Library in Cardiac Sonography Education

Introduction

In cardiac sonography education, laboratory time is among the most limited and instructionally valuable resources within the curriculum. Under the current instructional model, a significant portion of laboratory sessions is devoted to repeated live demonstrations of standard cardiac windows, measurement techniques, and troubleshooting corrections. While demonstration is necessary for initial modeling, repeated faculty-led demonstration does not consistently translate into independent scanning fluency.

In the existing structure, first-attempt competency pass rates in the cardiac scanning laboratory average approximately 62%, with nearly one-third of students requiring at least one remediation session prior to clinical placement. Faculty instructional logs indicate that live demonstration occupies approximately 50–60% of early laboratory sessions. These baseline indicators suggest that laboratory time is not being maximized for supervised psychomotor repetition—an essential element in ultrasound skill acquisition.

The proposed Crux innovation restructures laboratory instruction through a flipped-lab model supported by a structured, indexed, on-demand imaging library. The purpose is not technological enhancement for its own sake, but strategic reallocation of instructional time—shifting laboratory emphasis from repeated demonstration toward coached repetition and structured feedback. In ultrasound education, psychomotor skill development depends heavily on supervised hands-on repetition and immediate corrective guidance (Sidhu et al., 2017). By increasing deliberate scanning volume within supervised lab time, Crux seeks to improve clinical readiness prior to external placement.

Sustainable instructional change requires alignment among pedagogy, leadership practice, evaluation systems, and financial feasibility. This three-year implementation plan integrates change leadership theory, implementation science, clinical education research, and cost-effectiveness analysis to ensure the innovation becomes institutionalized rather than episodic.

Theoretical and Leadership Framework

Change Leadership and Coherence

Educational change literature emphasizes that innovation must be embedded within systems rather than introduced as isolated initiatives. Fullan (2016) argues that sustainable reform requires shared purpose, collaborative ownership, and continuous refinement. Accordingly, Crux will be introduced through structured faculty collaboration, transparent data review, and phased implementation rather than directive adoption.

In medical education settings, implementation science further distinguishes between intervention effectiveness and implementation effectiveness (Thomas et al., 2016). An instructional innovation must not only improve outcomes but also demonstrate adoption, fidelity, penetration, and sustainability within institutional routines.

Deliberate Practice in Clinical Skill Development

Expert performance develops through structured, feedback-intensive repetition (Ericsson, 2004). Ultrasound education research similarly emphasizes that competency acquisition depends on supervised psychomotor repetition with corrective guidance (Sidhu et al., 2017). The primary instructional shift within Crux operationalizes deliberate practice by reducing live demonstration time by approximately 40% and reallocating that time toward coached scanning repetitions.

Feedback Alignment and Faculty Calibration

Feedback effectiveness depends on clarity, specificity, and alignment with performance standards (Hattie & Timperley, 2007). In sonography laboratories, inconsistent correction language across instructors can delay skill acquisition. Twice-annual faculty calibration sessions and standardized performance rubrics will ensure consistent expectations and structured feedback delivery.

Evidence Base for Flipped Learning in Health Professions

A systematic review of flipped classrooms in undergraduate health professions education reported moderate positive effects on academic performance compared to traditional lecture-based instruction (Naing et al., 2023). Performance gains were strongest when pre-class materials were intentionally aligned with active in-class application.

Multimedia learning theory further supports segmented instructional design, demonstrating that breaking complex tasks into focused modules reduces cognitive overload and improves retention (Mayer, 2009). For sonography students—who must simultaneously integrate anatomy recognition, probe manipulation, and measurement precision—segmented imaging modules aligned to specific scanning objectives provide structured preparation prior to laboratory practice.

Crux applies these findings through indexed content organized by cardiac window, anatomical structure, measurement category, and troubleshooting scenario.

Research-Oriented Logic Model

Program Theory

If students complete segmented imaging modules prior to laboratory participation and laboratory time is systematically reallocated toward coached scanning repetition, then supervised scanning volume will increase. Increased repetition paired with calibrated feedback will improve first-attempt competency performance, reduce remediation frequency, and enhance early clinical independence.

Inputs

- Faculty instructional expertise

- Recording and editing equipment

- Learning management system infrastructure

- Institutional IT support

- Baseline competency and remediation data

Activities

- Development of indexed cardiac imaging modules

- Required pre-lab review integration

- Reduction of live demonstration time

- Faculty calibration sessions

- Pilot cohort implementation

- Ongoing performance and efficiency data collection

Implementation Outcomes (Proctor et al., 2011)

- Acceptability (faculty perception surveys)

- Adoption (percentage of instructors implementing model)

- Fidelity (adherence to demonstration reduction structure)

- Penetration (integration across cohorts)

- Sustainability (formal curriculum embedding)

Effectiveness Outcomes

Short-Term:

- Increased readiness quiz performance

- Increased supervised scanning repetitions

- Improved first-attempt competency rates

Long-Term:

- Enhanced clinical preceptor evaluations

- Reduced remediation sessions

- Increased early-rotation independence

Increasing first-attempt competency performance from 62% to approximately 75–80% would align laboratory preparation more closely with early clinical expectations.

Three-Year Implementation Plan

Year One: Development and Pilot

Baseline competency performance and remediation data will guide refinement of objectives. Segmented modules will be developed following multimedia learning principles (Mayer, 2009). Faculty planning sessions will align instructional language and evaluation standards.

A pilot cohort will implement the flipped-lab structure during the second semester. Evaluation will include readiness assessments, first-attempt competency rates, faculty time logs, and student perception surveys.

Year Two: Expansion and Validation

The model will expand across all first-year cohorts. Pre-lab preparation will be embedded into grading structures to ensure accountability. Calibration meetings will occur twice annually.

Performance targets include:

- 20–30% increase in first-attempt competency pass rates

- 25% reduction in remediation sessions

- Improved early clinical confidence ratings

Year Three: Institutionalization and Scalability

Crux will be embedded within curriculum governance documents and faculty onboarding processes. Adoption and fidelity metrics will be reviewed annually. Scalability to vascular and abdominal tracks will follow structured implementation capacity-building principles (Leppin et al., 2021).

Executive Return on Investment (ROI) Analysis

Educational innovation must demonstrate fiscal stewardship alongside academic benefit. Within contemporary higher education systems, instructional redesign must be evaluated not only for pedagogical impact but also for demonstrable return on investment, long-term sustainability, and alignment with institutional resource allocation models.

Financial Summary

Initial Startup Investment: $11,700
          Annual Maintenance Cost: $3,700
          Three-Year Total Cost: $22,800

Efficiency Gain Calculation

Projected efficiency gains are calculated based on a conservative reduction of approximately 2 faculty instructional hours per week during demonstration-heavy laboratory sessions across two 15-week semesters. At an estimated instructional cost of $50 per hour (inclusive of salary and fringe allocation), this represents approximately $1,500 per semester, or $3,000 annually in recaptured instructional capacity.

Additional projected gains reflect decreased remediation sessions, estimated at 20–25 faculty hours annually across cohorts. Combined, these adjustments yield an estimated $7,000 in annual instructional efficiency gains without increasing total workload.

Projected Three-Year Efficiency Gains: $21,000

Break-even occurs during Year Two under conservative projections.

Beyond direct cost recovery, Crux represents instructional productivity reallocation. Demonstration time yields diminishing marginal returns when repeated excessively. Reallocating that time toward coached repetition increases instructional yield per laboratory hour.

Indirect benefits include reduced faculty overload, potential delay of additional hiring, strengthened clinical partnerships, and enhanced program competitiveness.

Risk Management

Risks include faculty resistance, inconsistent student pre-lab engagement, technological fatigue, and budget limitations. Mitigation strategies include collaborative planning, graded readiness assessments, phased expenditures, and annual content review cycles.

Sustained faculty calibration remains central to preventing instructional variability (Sidhu et al., 2017).

Conclusion

Crux represents a deliberate, data-informed shift toward performance-centered laboratory instruction in cardiac sonography education. Grounded in deliberate practice theory, multimedia learning research, implementation science, and discipline-specific clinical education literature, the innovation aligns pedagogical rigor with fiscal responsibility.

Over three years, the plan transitions from pilot implementation to institutional embedding. Startup costs remain modest, recurring costs are controlled, and break-even occurs within two academic cycles. More importantly, reallocating laboratory time toward coached repetition strengthens the conditions under which clinical expertise develops.

Crux positions the program for sustained instructional improvement, enhanced clinical readiness, and long-term institutional advancement.

References

Ericsson, K. A. (2004). Deliberate practice and the acquisition and maintenance of expert
          performance in medicine and related domains. Academic Medicine, 79(10), S70–S81.

Fullan, M. (2016). The new meaning of educational change (5th ed.). Teachers College Press.

Hattie, J., & Timperley, H. (2007). The power of feedback. Review of Educational Research,
          77(1), 81–112.

Leppin, A. L., Baumann, A. A., Fernandez, M. E., Rudd, B. N., Stevens, K. R., Warner, D. O., Kwan, B. M., & Shelton, R. C. (2021). Teaching for implementation: A framework for building
          implementation research and practice capacity within the translational science workforce. Journal of Clinical and Translational Science, 5(1), e147. https://doi.org/10.1017/cts.2021.809
Mayer, R. E. (2009). Multimedia learning (2nd ed.). Cambridge University Press.

Naing, C., Whittaker, M. A., Aung, H. H., Chellappan, D. K., & Riegelman, A. (2023). The
          effects of flipped classrooms to improve learning outcomes in undergraduate health
          professional education: A systematic review. Campbell Systematic Reviews, 19(3), e1339.
          https://doi.org/10.1002/cl2.1339

Proctor, E., Silmere, H., Raghavan, R., Hovmand, P., Aarons, G., Bunger, A., Griffey, R., & 
          Hensley, M. (2011). Outcomes for implementation research: Conceptual distinctions, 
          measurement challenges, and research agenda. Administration and Policy in Mental 
          Health and Mental Health Services Research, 38(2), 65–76. 
          https://doi.org/10.1007/s10488-010-0319-7

Sidhu, P. S., Brabrand, K., Cantisani, V., et al. (2017). EFSUMB recommendations on education
          and training in ultrasound. Ultraschall in der Medizin, 38(4), 364–369. 
          https://doi.org/10.1055/s-0043-111663

Thomas, D. C., Berry, A., Djuricich, A. M., et al. (2016). What is implementation science and 
          what forces are driving a change in medical education? Journal of Graduate Medical 
          Education, 8(4), 593–600. https://doi.org/10.4300/JGME-D-16-00075.1